## Sheet1
Sl. No | System | Type | Start Date | End Date | Team |  | Description | Sprint | Priority | Status | JIRA
1 | Ordering | Critical Bug |  |  |  |  | Unable to Search Existing customer in VBizz | Sprint 1 | 1-Critical | Completed | http://jira04.switchlab.com/browse/VBP-250
2 | Ordering | Improvement |  |  |  |  | SIM Card Type (Normal, Micro, Nano) Selection For all of the flows ( Existing Customer, New Customer, Individual and shared) | Sprint 2 | 1-High | Open | http://jira04.switchlab.com/browse/VBP-199
3 | Ordering | BUG |  |  | SIVA -8 hrs |  | Ordering Flow - Payment server error | Sprint 3 | 1-High |  | http://jira04.switchlab.com/browse/VBP-237
Step 1: User orders a mobile and fills all details
Step 2: Enters payment details in credit card
Step 3: System is taking time for payment and shows loading symbol (Buffering)
Step 4: User clicks back button – Payment server error
4 | Ordering | BUG |  |  | Dharma - 2 hrs |  | Invalid Security code | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/VBP-236
Step1: Enter more than 5digit no in security code
Step 2: Enter less than 5 digit no in security code
Step3:invalid input was accepted by the create customer page
5 | Ordering | BUG |  |  | Siva - 5 hrs |  | Issue 1: Add 2014 to the start date of the credit card field: | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/VBP-253
This value should be dynamically fetched based on the current year with previous 10 year including the current year.
Issue 2:
a. Give proper credit card number but the start and end date is incorrect
b. Give proper credit card number, start and end date, but CVV number is incorrect
c. Give invalid credit card number
6 | Ordering | BUG |  |  | Dony - 3 hrs |  | Even though we add additional charge in Order Information Page, the additional charge doesn’t get added with the Total amount to be paid. Once Add Charge button is pressed a pop up message appears stating additional charges are added but additional charge doesn’t get reflected with the total amount.(Also check the same in CRM side). | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/VBP-251
7 | Ordering | BUG |  |  | Dony - 1 hrs |  | Issue - Incorrect amount is shown while adding 'Automated Operator' | Sprint 3 | 2- High |  | http://jira04.switchlab.com/browse/VBP-256
8 | Ordering | BUG |  |  | Dony -2 Hrs |  | When a Handset is removed in Customer’s Basket page for a Sim + Handset Order still the order gets placed. | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/VBP-257
9 | Ordering | BUG |  |  | Dony -2 Hrs |  | When we try and remove an item from selected items the item gets removed from the list but it goes back and again gets reflected in select plan table. Order once removed should completely go of the page. | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/VBP-259
10 | Ordering | BUG |  |  | Not required |  | Selection of address list by its first letter | Sprint 3 | 3-Normal |  | http://jira04.switchlab.com/browse/VBP-239
Step1: open Create New company page from orders
Step2: select the address list by in first word
11 | Ordering | BUG |  |  | Dharma - 1 hrs |  | Selected user number drop down was not displayed in selected plan details | Sprint 3 | 3-Normal |  | http://jira04.switchlab.com/browse/VBP-245
Step1: Select the plan needed in shared plan
Step2: in selected plan details selected user number drop down was not displayed
12 | Ordering | BUG |  |  | Not required |  | Selection of shared plan: | Sprint 3 | 3-Normal |  | http://jira04.switchlab.com/browse/VBP-246
Step1: select shared plan and select needed plan from the list
Step2: selected plan was displayed in selected plan table
Step3: unselected plan was displayed in order summary (This happen rarely)
13 | Ordering | BUG |  |  | Dharma - 1 hrs |  | In Line Rental once you proceed after filling up the address there is something called New Line – One off Charge, once this is selected you would see the following page here if the Customer is mentioning a required date then it should be greater than present date. In this case it's accepting previous days date as well. | Sprint 3 | 3-Normal |  | http://jira04.switchlab.com/browse/VBP-252
14 | Ordering | Improvement |  |  | Dharma - 6 hrs |  | When Prospective customer wants to complete the order, then CS should be able to edit the order details | Next Sprint | 2-Medium |  | To be added
15 | Ordering | New Feature |  |  | Not required |  | Flow change in Ordering | Next Sprint | 2-Medium |  | To be added
(1) Add ‘Save as Prospective customer’ button in the ‘Company details’ page and
(2) Split the Payment processing from “Create Company Details” to next page as step 2
16 | Ordering | BUG |  |  | Dharma - 3 hrs |  | : In DSL Checker when a Landline Number and Post code is entered and validated nothing happens, no action is performed. Even after clicking validate it stays on the same page. | Next Sprint | 2- High |  | http://jira04.switchlab.com/browse/VBP-258
17 | Ordering | BUG |  |  | SIVA-1 hr |  | Failure of Drop down function | Next Sprint | 3-Normal |  | http://jira04.switchlab.com/browse/VBP-240
Step1: select payment-credit card page from order
Step2:select country drop down list
18 | Ordering | BUG |  |  | SIVA-1 hr |  | Selection of product | Next Sprint | 3-Normal |  | http://jira04.switchlab.com/browse/VBP-247
Step1: Select plan and no of users the Page movement button was not highlighted and not functioning
19 | Ordering | BUG |  |  | SIVA-2 hr |  | Accepting Invalid input | Next Sprint | 3-Normal |  | http://jira04.switchlab.com/browse/VBP-249
Step1: in order information of individual plan enter invalid input for promo code and reason for not completing order
Step2: click on make payment button
Step3: the process continuous to next page with invalid input
20 | Ordering | BUG |  |  | Dharma- 1 hr |  | After selecting plans and product then clicking Next its redirect to bundle page there Click on Back and again Click on Next its directly goes to Order summary page without the ordered items (as shown in SC:3) | Next Sprint | 2- High |  | http://jira04.switchlab.com/browse/VBP-261
21 | Ordering | BUG |  |  | Dharma- NA |  | While selecting a bundle from existing group it's should alert the user with "Bundle you selected already exists" instead of "you need to select a plan first". | Next Sprint | 2- High |  | http://jira04.switchlab.com/browse/VBP-262
22 | Ordering | BUG |  |  | Dony- 3 Hrs |  | While Click on Select more product and select the new items what you want to order that's not adding with current ordered items. | Next Sprint | 2- High |  | http://jira04.switchlab.com/browse/VBP-263
23 | Ordering | BUG |  |  | Dharma-2 hrs |  | In order summary, I clicked on the plus sign to see the bundles chosen and I wanted to remove one or two bundle while clicking on Remove button the bundles not removed and I refreshed the bundle package it crashed the User Interface UI. | Next Sprint | 2- High |  | http://jira04.switchlab.com/browse/VBP-264
24 | Ordering | BUG |  |  | Dharma-3 hrs |  | While Ordering IP Phone, after Selecting number of users and click on Select in Add Switchboard Pop up Window, Select number of users will be displayed in Selected switchboard below. After clicking on cancel button, the number of users selected and the number of users displayed differs in the selected switchboard summary. | Next Sprint | 2- High |  | http://jira04.switchlab.com/browse/VBP-265
25 | Ordering | BUG |  |  | Dharma-3 hrs |  | After Ordering Shared plan, I selected "Select more product" button in customer basket page redirected to Product page and there I selected Mobile->individual plan and selected the number of user and when I Select "select Plan" button it shows a alert message and I click on OK button in the alert box. Then if I click on Next button again the Alert message should be display or else "Server Error" will display because user cannot select Shared and Individual plan at the same time. | Next Sprint | 2- High |  | http://jira04.switchlab.com/browse/VBP-266
26 | Ordering | BUG |  |  | Siva - 5 hrs |  | DD form is requested for payment and I clicked "Make payment" button and it redirected to Credit card Payment page. Here I given credit card details with "wrong security code" and clicked Confirm button, the page redirected to payment confirmation page while clicking on confirm button in that page, it showed "Server Error" | Next Sprint | 2- High |  | http://jira04.switchlab.com/browse/VBP-267
[5 empty] | SI VA |  | 24 Hrs - 3 Days
[5 empty] | DONY |  | 24 Hrs - 3 Days
[5 empty] | DHARMA |  | 16 Hrs - 2 Days + 1 Day
Sl. No | System | Type |  |  |  |  | Description | Sprint | Priority | Status | JIRA
1 | CRM | Finance - Bug |  |  |  |  | Company is not appearing as ‘Active customer’ after finance approval | Sprint 1 | 1-High | Completed | http://jira04.switchlab.com/browse/URM-249
2 | CRM | Bug |  |  |  |  | Deskphone Provisioning Issue | Sprint 1 | 1-High | Completed | http://jira04.switchlab.com/browse/URM-256
3 | CRM | Finance |  |  |  |  | Edit ‘Out of Plan limit’ – CS should be able to manually edit this option | Sprint 1 | 2-High | Completed | http://jira04.switchlab.com/browse/URM-255
4 | CRM | SIM Details - Bug |  |  | Not required |  | SIM Replacement is not functional | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/URM-251
http://jira04.switchlab.com/browse/URM-250
5 | CRM | SIM Details - Improvement |  |  | Dony - 5 hrs |  | Customer - Products - Mobile Plans - Actions - SIM Details | Sprint 2 | 1-High | Open | http://jira04.switchlab.com/browse/URM-173
6 | CRM | Payment Bug |  |  |  |  | Error while making payment via credit card | Sprint 2 | 1-High | Completed | http://jira04.switchlab.com/browse/URM-253
7 | CRM | Bills |  |  |  |  | Bills not showing any info for active customer. | Sprint 2 | 1-High | Completed | http://jira04.switchlab.com/browse/URM-262
9 | CRM | Finance |  |  |  |  | While searching with rejected status nothing is displayed in Finance Tab in CRM. The Rejected orders are not getting tracked in finance. | Sprint 2 | 2-High | Completed | http://jira04.switchlab.com/browse/URM-260
The status in customers tab should show appropriate status such as:
• “Rejected by Finance” when finance rejects the order.
10 | CRM | Bug |  |  |  |  | The status in customers tab should show appropriate status such as: | Sprint 2 | 2-High | Completed | http://jira04.switchlab.com/browse/URM-261
• “Rejected by Finance” when finance rejects the order.
• “Awaiting Finance approval” when finance has not yet approved the order.
12 | CRM | Bug |  |  | Dony - 5 hrs |  | Error on direct debit option set-up | Sprint 2 | 2-High | Open | http://jira04.switchlab.com/browse/URM-263
13 | CRM | Bug |  |  |  |  | Issue 1: Unable to set-up direct debit option in "Customers -> Direct Debit" tab: | Sprint 2 | 2-High | Completed | http://jira04.switchlab.com/browse/URM-245
Submit button is not functioning
Issue 2: Unable to perform "set not in use" in Detail page of Direct debit option in "Customers -> Direct Debit" tab:
Actual: Stored procedure error is occurring
14 | CRM | Bug |  |  | Dony - 16 Hrs |  | Deskphone Auto-provisioning is not working for Aastra and Grandstream | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/UFM-452
15 | CRM | Bug |  |  | Not required |  | On clicking product -> External number button shows “ 404 errors” | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/URM-230
[7 empty] | This error was occurs in other tab also (occurs occasional) |  |  |  | http://jira04.switchlab.com/browse/URM-265
16 | CRM | Bug |  |  | Magendiran - 3 hrs |  | Finance-> Orders->click order item | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/URM-233
(Details record not found and internal server error)
Two error messages occurs UN expectedly (Rare cases)
17 | CRM | Bug |  |  | Magendiran - 3 hrs |  | Click order->select order from list->click more info | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/URM-234
The was not displayed
orders->click the list -> more info button-> refresh the page
The table was displayed as shown below
18 | CRM | Bug |  |  | Magendiran - 3 hrs |  | Direct Debit status is not in sync in finance tab and the DD details is not reflecting in MyAccount | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/URM-264
19 | CRM | Bug |  |  | Magendiran - 3 hrs |  | When an order is placed sometimes it doesn’t reflect under the Order tab in Finance. It’s dosen’t happen always. | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/URM-266
20 | CRM | Bug |  |  | Not required |  | Performance issue, every click action takes a long time to process. | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/URM-270
21 | CRM | Bug |  |  | Magendiran - 5 hrs |  | The issues (Scenario 1 and Scenario 2)given in document can be rectified by having an Auto Refresh every time an action is taken, simultaneously Refresh Button given in every tab should work. | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/URM-247
22 | CRM | Bug |  |  | Magendiran- NA |  | Drop down name should display | Sprint 3 | 3-normal |  | http://jira04.switchlab.com/browse/URM-226
“Select banks”
23 | CRM | Bug |  |  | Magendiran- 2 Hr |  | Entering alphabets in telephone text the value are accepted and in type text space are accepted | Sprint 3 | 3-normal |  | http://jira04.switchlab.com/browse/URM-228
Customers -> more info
24 | CRM | Bug |  |  | Magendiran- 1 Hr |  | Order detail page was not as expected | Sprint 3 | 3-normal |  | http://jira04.switchlab.com/browse/URM-232
Actual - screen display doc was attached
Step1: finance– Order – Order Details.
25 | CRM | Bug |  |  | Magendiran- NA |  | Admin details: click edit | Sprint 3 | 3-normal |  | http://jira04.switchlab.com/browse/URM-235
Enter space in admin contact name input was accepted
26 | CRM | Bug |  |  | Magendiran- 1 Hr |  | Direct Debit spell check | Sprint 3 | 3-Normal |  | http://jira04.switchlab.com/browse/URM-237
Direct Debit -> DD operation
Below table should name as DD status.
27 | CRM | Bug |  |  | Dony -5 Hrs |  | In Line Rental & Broadband tab in ORDER (CRM) the Line Rental status is completed but even though the Broadband status is still in pending state, the company in Order tab is showing as "Fully Provisioned". | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/URM-273
28 | CRM | Customer - Bug |  |  | Magendiran - 8 Hrs |  | Customer > product >mobile plans >select action >upgrade Action from CRM is not reflecting on MyAccount | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-86
(use-case needs to be enhanced)
29 | CRM | Improvement |  |  |  |  | Suspend/Cancel an account and Reactivate an account | Next Sprint | 2-High |  | To be added
30 | CRM | Finance |  |  |  |  | Manual Request bill adjustments or Refunds by Finance | Next Sprint | 2-High |  | To be added
31 | CRM | Finance - Improvement |  |  |  |  | Create custom view in Finance tab – for Approval, Rejected statuses. | Next Sprint | 2-High |  | To be added
32 | CRM | Post Request - New Feature |  |  | Dharma - 24 Hrs |  | Post Request | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-186
33 | CRM | Customer - Improvement |  |  | Magendiran - 8 hrs |  | Customer - Products - Mobile - Plan Type | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-123
34 | CRM | Finance - Improvement |  |  | Dony - 5 hrs |  | CRM- Line Rental & Broaband Pop up- Charge | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-154
35 | CRM | Customer - Improvement |  |  | Dony - 5 hrs |  | Customer - More Info Improvement | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-136
36 | CRM | Customer - Bug |  |  | Dony - 5 hrs |  | CRM - Customers Tab - My Account Users Tab Content | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-204
37 | CRM | Notification - Improvement |  |  | Dharma - 18 hrs |  | Email Notification - Triggers and flow | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-103
38 | CRM | Finance - Improvement |  |  | Dony - 40 Hrs |  | Integration of Bill - Payment History, Payment Profile, Direct Debit Operations | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-200
39 | CRM | Customer - Improvement |  |  | Dony - 8 hrs |  | Port In Mobile Number | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-122
40 | CRM | Bills - Improvement |  |  | Dharma - 18 hrs |  | Invoice Design | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-126
41 | CRM | Bug |  |  | Dony - 5 Hrs |  | There is no way to check the details of the order placed by a prospective customer. This requirement will help the CS agent to inform the customer about the current order by referring the CRM. | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-267
42 | CRM | Bug |  |  | Dony - 5 Hrs |  | In Query under customers tab we need to add one more search criteria “Mobile / LL no.” to search an existing customer. | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-268
43 | CRM | Bug |  |  | magendiran - 12 hrs |  | In proposed system a bills tab is needed next to the My account users tab with same functionality as of Bills tab in finance. | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-269
44 | CRM | Customer - Improvement |  |  | Not required |  | The More Info page should have the same interface as Create New Page in ordering system. | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-248
45 | CRM | Bug |  |  | Magendiran - 8 hrs |  | After entering Edit button all fields are in company details are empty | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-222
After creating new company
Crm->customer->more info-> edit
46 | CRM | Bug |  |  | Magendiran - 8 hrs |  | Customer ->order click details | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-225
In detail order items click cancel button the order was not cancelled
47 | CRM | Bug |  |  | Dharma - 3 hrs |  | On clicking refresh button no record was display | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-231
CRM->Finance-> Refresh
48 | CRM | Bug |  |  | Dony - 12 hrs |  | Click Direct debits->new direct debit tab from customer | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-236
New form open enter the fields
Click submit button. Process was not preceded
49 | CRM | Bug |  |  | Magendiran - 1 hrs |  | Country name: numeric value are accepted | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-243
51 | CRM | Bug |  |  | Magendiran - 1 hrs |  | Finance -> order | Next Sprint | 3-normal |  | http://jira04.switchlab.com/browse/URM-229
Order date and order id was in valid(occurs un expectedly)
52 | CRM | Bug |  |  | Magendiran - 1 hrs |  | Drop down text editable | Next Sprint | 3-normal |  | http://jira04.switchlab.com/browse/URM-220
Customer-> product-> selection action
53 | CRM | Bug |  |  | Magendiran - 1 hrs |  | Add a valid error message (kindly check with product team) | Next Sprint | 3-normal |  | http://jira04.switchlab.com/browse/URM-221
Dispatch-> royal mail reference
Enter the mail id
Click submit
54 | CRM | Bug |  |  | Magendiran - 1 hrs |  | Incomplete calendar | Next Sprint | 3-normal |  | http://jira04.switchlab.com/browse/URM-238
In Add New company page in contact field calendar field Date was not proceeded and march month was in complete .
55 | CRM | Bug |  |  | Magendiran - 2 hrs |  | Search customer by its company name | Next Sprint | 3-normal |  | http://jira04.switchlab.com/browse/URM-244
Select the company name
Search company in customer query
56 | CRM | Bug |  |  | Not required |  | CRM-Customers-Date issue in More Info and Page not Refreshing automatically | Next Sprint | 3-normal |  | http://jira04.switchlab.com/browse/URM-246
57 | CRM | Bug |  |  | Dharma - 1 hrs |  | Crm-> customer->direct debit-> details | Next Sprint | 4-minor |  | http://jira04.switchlab.com/browse/URM-223
Direct debit uploaded files shows alignment issues
58 | CRM | Bug |  |  | Dharma - NA |  | Button should displayed as “order details” | Next Sprint | 4-minor |  | http://jira04.switchlab.com/browse/URM-224
59 | CRM | Bug |  |  | Dharma - NA |  | File name exceeds out of box | Next Sprint | 4-minor |  | http://jira04.switchlab.com/browse/URM-227
When file was uploaded
CRM->customer->Direct Debit details-> details
60 | CRM | Bug |  |  | Dharma - 5 Hrs |  | In Customers tab, Company details are not recorded for Prospect customers. And While updating details in Company, Billing, Admin and Dispatch details the alert message was showing wrongly. | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-275
61 | CRM | Bug |  |  | Dharma - 8 Hrs |  | Without clicking on "Save as Prospective Customer" button, the details are recorded in CRM customers tab as in Prospect Status. | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-276
Expected: Ordering system should save order details only after the user clicks on "Save as Prospective customer" button and the same should reflect in CRM
62 | CRM | Bug |  |  | Dharma - 5 Hrs |  | Althought the LL order has been completed and the status has been changed to “Completed” still we are getting this below mentioned error message while selecting the “Committed” status for BB. | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-277
63 | CRM | Bug |  |  | Dharma - 8 Hrs |  | Customers are not getting email notification for some scenarios | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-278
64 | CRM | Bug |  |  | Dharma - 1 Hrs |  | Filter Pop Up menu not Clearly Visible in UI | Next Sprint | 2-High |  | http://jira04.switchlab.com/browse/URM-279
[5 empty] | Dony |  | 116 Hrs - 15 Days
[5 empty] | Magendiran |  | 72 Hrs - 9 Days
[5 empty] | Dharma |  | 90 Hrs - 12 days
Sl. No | System | Type |  |  |  |  | Description | Sprint | Priority | Status | JIRA
1 | My Account | MyAccount – Personal Users |  |  |  |  | Unable to receive SMS on UF MyAccount Register flow on MyAccount | Sprint 1 | 2-High | Completed | http://jira04.switchlab.com/browse/UFM-395
Bug
2 | My Account | Billing |  |  | Dharma - 8 hrs |  | Billing and Payment Overview | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-284
Improvement
3 | My Account | Billing |  |  | Dharma - 8 hrs |  | Billing and Payment - Bill History | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-141
Improvement
4 | My Account | Billing |  |  | Siva - 24 hrs |  | Billing and Payment - Pay Now | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-285
Improvement
5 | My Account | Call History |  |  | Dharma - 5 Hrs |  | Unable to view the call history in MyAccount interface | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-397
6 | My Account | Call History - Improvement |  |  | Dharma - 5 Hrs |  | Call History Mobile and Desk Phone Improvement | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-259
7 | My Account | Call History - Bug |  |  | jaya - 8 Hrs |  | Performance Issue of Call History | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-299
8 | My Account | Feature |  |  | Ram |  | My Account - Deskphone Directory Management | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-333
9 | My Account | Feature |  |  | Ram |  | My Account - Online phone Directory Management | Sprint 1 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-334
10 | My Account | Feature |  |  | Ram |  | Call Queue | Sprint 2 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-336
11 | My Account | Feature |  |  | Magendiran |  | Switchboard – Automated Operator | Sprint 2 | 1-High | Open | http://jira04.switchlab.com/browse/UFM-337
12 | My Account | Bug |  |  | Jaya - 5 Hrs |  | Incorrect Domain ID mapping in MyAccount | Sprint 2 | 1-Critical | Open | http://jira04.switchlab.com/browse/UFM-451
13 | My Account | MyAccount |  |  |  |  | All Extension is not visible in MyAccount after provisioning from CRM | Sprint 2 | 1-High | Completed | http://jira04.switchlab.com/browse/URM-259
14 | My Account | MyAccount – Personal Users |  |  | Ram - 40 Hrs | Nat/Ram | Personal My Account With New Design | Sprint 3 | 2-High |  | http://jira04.switchlab.com/browse/UFM-198
|  | Improvement | [8 empty] | Reference:
MyAccount Registration Flow: http://jira04.switchlab.com/browse/UFM-202
15 | My Account | Feature |  |  | Ram - 8 Hrs |  | Conference Room | Sprint 3 | 1-High |  | http://jira04.switchlab.com/browse/UFM-382
16 | My Account | Bug |  |  | Ram - 8 Hrs |  | A customer orders “Virtual” number using MyAccount, however Direct Debit information is not added on the MyAccount - thus a warning message is shown. But in CRM, the feature is getting added incorrectly. | Sprint 3 | 1-High |  | http://jira04.switchlab.com/browse/UFM-414
17 | My Account | Overview - Improvement |  |  | Ram - 12 Hrs |  | General Overview | Next Sprint | 1-High |  | http://jira04.switchlab.com/browse/UFM-149
18 | My Account | Payment Bug |  |  | Siva - 8 Hrs |  | Unable to make bill payment from MyAccount interface | Next Sprint | 1-High |  | http://jira04.switchlab.com/browse/UFM-396
19 | My Account | Admin Functionality - |  |  | Ram - 24 Hrs |  | User Rights Management | Next Sprint | 1-High |  | To be added
New Feature
20 | My Account | Feature |  |  | Not required |  | Fax Management | Next Sprint | 1-High |  | To be added
21 | My Account | Feature |  |  | Ram - 12 Hrs |  | Call from Browser through Deskphone only - through Browser Extension | Next Sprint | 1-High |  | Pending
22 | My Account | Feature |  |  | Ram - 18 Hrs | Pending/wait | My Account - View Call/SMS Recording | Next Sprint | 1-High |  | http://jira04.switchlab.com/browse/UFM-335
23 | My Account | Feature |  |  | Ram - 12 Hrs | Pending/Darma | Restart Functionality – from MyAccount | Next Sprint | 1-High |  | http://jira04.switchlab.com/browse/UFM-338
1 | Other System | Bug |  |  |  |  | Email Notification Link is down - http://192.168.1.230:19991/ | Sprint 3 | 2-High | Open | http://jira04.switchlab.com/browse/URM-257
2 | Notification | Bug |  |  | Ram - 24 hrs |  | Please find the attached email for SMS issue. | Next Sprint | 2-High | Open | http://jira04.switchlab.com/browse/URM-274
Customer (Rishabh's account) received the following SMS during the month of April:
Date Message Comments
18th April You have 100% credit limit - User didn't receive SMS for 80% credit limit - need to check
User extends credit limit on 18th April
30th April 00:59 AM You have 80% credit limit User received the 80% SMS and it is fine
1st May 1:11 AM You have 80% credit limit -User received the same SMS again - need to check why it was resend again
[5 empty] | Dharma |  | 26 Hrs - 4 Days
[5 empty] | Siva |  | 32 Hrs - 4 days
Magendiran
[5 empty] | Ram |  | 158 Hrs - 20 Days
[5 empty] | Dharma |  | 19 Days
[5 empty] | Siva |  | 7 Days ( Partial involvemnet with UF project)
[5 empty] | Magendiran |  | 9 Days ( To be shared with other tasks and bugs )
[5 empty] | Ram |  | 20 Days
[5 empty] | Dony |  | 18 Days